## Sheet1
|  | Dec | 2 | 3 | 4 | Jan | 2 | 3 | 4 | Feb | 2 | 3 | 4 | Mar | 2 | 3 | 4
Ribbon
Sketch jig
Manufactur jig
Test wind
Make planes
QA
Locate sources and define work plan
Complete Rad safety paper work
Construct x-y stage
Complete lab safety
Write software to run QA test
Run QA tests
Camera & DAQ
Source camera
Design and construct mount
Workshop
Venue logistics
Invitations
Speakers
Laser testing