## Slide 1: LhARA proposal

## Slide 2: LhARA full Conceptual Design Report proposal
Proposal for 2—year programme; + 3 year forward look [coincident with preliminary phase programme]
Scope:
  2 year:
    Complete Conceptual Design Report for LhARA
    Key steps in the initial risk-mitigation programme:
      Measurement of spectra produced at laser-driven ion source
        And, benchmarking against simulation
      Experimental programme leading to specification and manufacture of second plasma-lens prototype
        Second prototype to demonstrate plasma dynamics has been understood and controlled; beam test “icing on cake”
      Proof of principle of ion-acoustic imaging for in-vitro radiobiological experiments
        Plan for next steps in the pre-construction phase R&D programme and considerations of what takes it to a clinical system
      Complete design for vertical beam line for end-station system development
        And, consultation to lead to specification of end-station developments required
      Design and integration of LhARA facility required to:
        Deliver completed LhARA CDR
        Define next steps in the risk mitigation R&D programme to be carried out in the pre-construction phase (next 3 years)
  5 year:
    Full technical design report for Stage 1:
      Supported by pre-construction phase risk-mitigation programme
    Initial technical design for Stage 2:
      Risk mitigation programme definition to be carried out in parallel to the Stage 1 build
      Programme to deliver full TDR for stage 2
    Initial ideas for “Stage 3”:
      Roll-out to enhance practice; elements of full system, system prototypes, …

## Slide 3: LhARA Conceptual Design Report proposal
LhARA “project organisation”:
Proposed for proposal and Preliminary phase
Summarised below using “particle physics collaboration model”
Co-spokes people:
  Giacca (OIRO, Oxf), Long (ICL/STFC/JAI)
Co-project-managers:
  Parsons (Liv), Whyte (Str/CI)
Work packages and work-package managers:
    Project Management: Parsons (Liv), Whyte (Str/CI)
      Project Office: D. Kordopati (ICL)
    Laser-driven proton and ion source: Dover (ICL/JAI), + Gray (Str)
    Proton and ion capture: Charlton (Swn), Bertsche (Manch/CI)
    Real-time dose-deposition imaging: Bamber (ICR), Mattheson (STFC/PPD)
    Novel, automated end-station development: McLauchlan (ICL NHS), Price (Brm)
    Facility design and integration: Pasternak (ICL/JAI), + TBC
ccap-lhara-wpm <ccap-lhara-wpm@imperial.ac.uk>

## Slide 4: Proposal structure
Scientific proposal:
  Scientific need:
    Clinical drivers, biololgical, medical, accelerator and physical science
  Multidisciplinary approach, incremental & transformational impact
  Scientific and technological programme
  Work package description
    With high-level milestones & overview of costs
Management annexes:
  Project management:
    Including Project organisation, project specification, cost, & financial management plan, schedule, milestones & decision points, critical path, (change control), quality plan, monitoring progress against milestones, risk analysis & risk management plan, safety plan, stakeholder plan, procurement strategy, staffing strategy, document control, evaluation strategy
  Work package definitions:
    Work-package description including deliverables and milestones, staff, costs analysis

## Slide 5: Some preparatory work
Costing tool will always be under development, but:
  For info, this is the “data structure”
Likelihood is only Colin, Dion, and KL need to worry about it
Builds on planning done for pre-CDR
WPMs send i/p to “Grand Gantt Chart” (GCC) which will be compiled and managed by Dion

## Slide 6: Proposal timeline
Working backwards:
  Monday 01Nov21:
    Proposal complete (ink drying)
  Monday 04Oct21:
    First drafts of text of proposal and management annexes complete
      Implies iteration of costs and time-line analysis
  Monday 13Sep21:
    Scope of proposal and w/s define:
      Implies initial costing and initial time-line analysis
  Tuesday 20Jul21 (today!):
    Launch of proposal preparation

## Slide 7: Cost sheet
Cost-sheet by work package:
  Owned by work-package managers
Python code prepared to automate financial reporting
  Daughter of the “big spreadsheet” that some may remember fondly