## Sheet1
Work Package | Gantt Chart Line number | Milestone Number | Milestone name | Current Date | New Date
WP2 | 458 | M2.1 | Prediction of optimised proton source parameters for 100+ TW laser systems based on hydrodynamic and kinetic simulations | 2023-10-01 | 2023-09-14 | CM3
| 459 | M2.2 | First SCAPA ion source simulations and experiment completed. | 2024-04-01 | 2024-03-14 | CM4
WP3 | 481 | M3.1 | Validate plasma simulations with existing Swansea experimental set-up | 2023-04-03 | 2023-03-14 | CM2
| 482 | M3.2 | Progress report of large diameter plasma experiments and simulations | 2024-04-14 | 2024-03-14 | CM4
| 483 | M3.3 | Next generation plasma lens testbench design | 2024-09-30 | 2024-09-19 | CM5
WP4 | 533 | M4.1 | Geant4 simulations of beam energy deposition profile | 2024-04-01 | 2024-03-14 | CM4
| 534 | M4.2 | Acoustic sensor array design | 2024-09-30 | 2024-09-19 | CM5
WP5 | 552 | M5.1 | Initial report on the user requirements for the in-vitro and in-vivo end stations. | 2023-03-31 | 2023-03-16 | CM2
| 553 | M5.2 | Report on the beam-monitoring technology for LhARA. | 2023-09-29 | 2023-09-14 | CM3
| 554 | M5.3 | Second report on the user requirements for the in-vitro and in-vivo end stations. | 2024-03-30 | 2024-03-14 | CM4
WP6 | 612 | M6.1 | Early review of R&D work towards LhARA CDR (6 months) | 2023-04-03 | 2023-03-16 | CM2
| 613 | M6.2 | Interim review of R&D work towards LhARA CDR (12 months) | 2023-10-02 | 2023-09-14 | CM3
| 614 | M6.3 | Final review of R&D work towards LhARA CDR (18 months) | 2024-04-02 | 2024-03-14 | CM4
| 34 |  | CM2 | 2023-03-15 |  | 481, 552, 612
| 35 |  | CM3 | 2023-09-13 |  | 458, 553, 613
| 36 |  | CM4 | 2024-03-13 |  | 459, 482, 533, 554, 614
| 37 |  | CM5 | 2024-09-11 |  | 483, 534