## Top Level
Blank | Number | Relevant WPs | Name | Description | Likelihood | Impact | Score | mitigation | Mitigated Impact | Mitigated score | Comments | Significant Dates | Retirement date
| 1 | 2&3 | source+lens | Integration of source and Lens requires compromises which impact on final performance | 3 | 5 | 15
| 2 | 2,4&5 | Dose | Photo-acoustic signal cannot provide required fidelity | 2 | 5 | 10
| 3 | 1, All | Funding | Funding insufficient to maintain progress in all fields leading to no progress and loss of staff in particular work packages | 3 | 5 | 15
| 4 | 5&6 | Vertical beam line | Birmingham site requires compromises which reduce relevance of test | 2 | 3 | 6
| 5 | All, 1 | Relevance | Project strays from performance target such that relevance is lost | 2 | 5 | 10 | Bio/Med engagement through task in WP5 yrs 1-2 expanding to 0.5FTE time post yrs 3-5 | 1 | 5
| 6 | All, 1 | Relevance | Requirement changes such that project performance is no longer relevant | 1 | 4 | 4 | Project involvement in wider user treatment options through expert collaboration members active in radiation biology research field | 1 | 4
| 7 | All, 1 | Relevance | Patient input not favourable | 2 | 5 | 10 | Early involvement, meaningful consultation. Funding for 2 patient representatives though full 5 yrs of project, funds held in WP1 | 1 | 5
| 8 | [5 empty] | 0
| 9 | [5 empty] | 0
10
11
12
13
14
15
16
17
18
19
20

## WP1 - PO
Blank | Number | Name | Description | Likelihood | Impact | Score | mitigation | Mitigated Impact | Mitigated score | Comments | Significant Dates | Retirement date
| 1 | Funds | Funds awarded insufficient for full program | 5 | 4 | 20 | Prioritisation of work packages, cost/scope reduction measures within work packages | 2 | 10 | Bound to happen | Early 2022 | End project
| 2 | Staffing | Loss of critial staff effort | 3 | 3 | 9 | Dual Work Package Management team leads | 1 | 3 | Unlikely in short term, increasing risk depending on funds received | Early 2023 | End project
3

## WP2 - Source
Blank | Number | Name | Description | Likelihood | Impact | Score | mitigation | Mitigated Impact | Mitigated score | Comments | Significant Dates | Retirement date
| 3 | Source - Energy | Unable to deliver sufficient beam energy from source | 3 | 3 | 9 | Early testing regime. Option to use thin based slides | 2 | 6
| 4 | Source - Intensity | Unable to deliver sufficient beam intensity. | 3 | 3 | 9 | Early testing regime. Multiple shot treatment | 2 | 6
| 5 | Source - divergence | Unable to capture sufficient particles in beam due to un/mis understood source dynamics |  |  | 0 |  |  | 0
| 6 | Source - particle type | C6 yield low |  |  | 0 |  |  | 0

## WP5 Trial
WP$