## Project Inf. & Revison control
| Project Title | LhARA
| Project Managers | Jason Parsons, Colin Whyte.
| Document Name | 21_11_01_RiskReg
| Date | 2021-11-01
| Revision | 1.0
| Work Package 1 | Project Management
| Work Package 2 | Laser - driven source
| Work Package 3 | Proton and ion capture
| Work Package 4 | Ion - acoustic dose profiling
| Work Package 5 | Novel end - station development
| Work Package 6 | Facility design & integration
Revision history
Revision | Date | Revision description
1
2
3
4

## Scoring Criteria
Scoring criteria
Use these tables to define the criteria you will use to score risks on the project and agree this with the project office.
Probability scoring criteria: Likelihood of Risk Occuring
Qualitative Description | Definition/Criteria
Very unlikely | <20%
Unlikely | 20%-40%
Moderate | 40%-60%
Likely | 60%-80%
Very likely | >80%
Impact scoring criteria: What effect would the risk have if it did occur
Use quantitative criteria where possible eg. % of budget for cost, weeks/months delay for schedule.
Qualitative Description | Definition
Estimated impact if the risk does occur to:
| Cost | Schedule | Quality | Reputation
Very low | <1% over budget | Cannot deliver activity to plan, no significant impact to schedule. | Minimal or no consequence to quality of output. | Short term damage to project reputation.
Low | 1-5% over budget | Cannot deliver task to plan, no impact on interim milestone. | Minor reduction to quality, can be tolerated with little/no impact to customer. | Medium term damage to project reputation.
Moderate | 5-10% over budget | Cannot meet an interim milestone, no impact to customer milestone. | Significant quality reduction, complicates customer acceptance. | Long term damage to project reputation.
High | 10-20% over budget | No float remaining for key/customer milestone. | Quality of final output reduced, does not meet customer expectation. | Long term national damage to project & consortium reputation.
Very high | >20% over budget | Cannot meet a key/customer milestone. | Quality of final output severely reduced, falls significantly short of customer expectation. | Long term international damage to project & consortium reputation.

## Scoring Matrix
Scoring matrix: as defined by the formulas in the threats register
Impact
|  |  | Very low | Low | Moderate | High | Very high
|  | Score | 1 | 2 | 3 | 4 | 5
Probability | Highly likely | 5 | 5 | 10 | 15 | 20 | 25 | Green = 1-4
| Likely | 4 | 4 | 8 | 12 | 16 | 20 | Amber = 5-14
| Moderate | 3 | 3 | 6 | 9 | 12 | 15 | Red = >=15
| Unlikely | 2 | 2 | 4 | 6 | 8 | 10
| Highly unlikely | 1 | 1 | 2 | 3 | 4 | 5
|  |  | 1 | 2 | 3 | 4 | 5
Scoring matrix: as defined by the formulas in the registers
Impact
|  |  | Very low | Low | Moderate | High | Very high
|  | Score | 1 | 2 | 3 | 4 | 5
Likelihood | Very likely | 5 | 5 | 10 | 15 | 20 | 25 | Green = 1-4
| Likely | 4 | 4 | 8 | 12 | 16 | 20 | Amber = 5-14
| Moderate | 3 | 3 | 6 | 9 | 12 | 15 | Red = >=15
| Unlikely | 2 | 2 | 4 | 6 | 8 | 10
| Very unlikely | 1 | 1 | 2 | 3 | 4 | 5

## Top Level Risks
Blank | Number | Name | Description | Likelihood | Impact | Score | Mitigation | Mitigated Likelihood | Mitigated Impact | Mitigated score | Comments | Significant Dates | Retirement date
| 1 | Stakeholder engagement | Insufficient stakeholder engagement leading to a deterioration in relationships that impact on the project success. | 3 | 5 | 15 | Develop a multidiscipline stakeholder engagement plan for the project. Include relevant radiobiology, medical and patient representation in core project management | 3 | 3 | 9
| 2 | Project direction & governance | Project vision, aims and objectives are not clear and well communicated or are not followed. | 4 | 4 | 16 | Estabish a reputable consortium, steering group, consortium & project oversight committee in imlementation phase of the project lifecycle. | 1 | 4 | 4
| 3 | Project management | Inadequate project management. | 4 | 4 | 16 | Establish processes, methods, skills, knowledge and experience to achieve the LhARA project objectives according to the project acceptance criteria. Adopt ISO9001 or similar techniques to achieve quality assurance and control. | 1 | 4 | 4
| 3 | Performance specification parameters | Inadequate ion beam parameters specification to meet the Physics and Biolology requirements for the facility. | 3 | 5 | 15 | The project consortium consists of all the multidiscipline experts to understand the required parameters. | 1 | 5 | 5
| 4 | Technology choices | Choice of technologies does not allow delivery within acceptable timescales and leads to failure to meet the ion beam specification parameters. | 2 | 4 | 8 | Pick reliable technology that there is confidence that can be delivered within the project timescale. | 1 | 4 | 4
| 5 | Resources | Insufficient resources secured to deliver the project aims, project scope, quality or specifications to the required timescale. | 5 | 4 | 20 | Request adequate resources based on experience of delivering similar multidiciple facilities with comparable technical complexity, address key callenges in the Conceptual Design Report (CDR) to those identified in the pre - CDR phase. | 4 | 4 | 16
| 6 | Project deliverables | Project deliverables not achieved to acceptance criteria. | 4 | 4 | 16 | Set realist deliverables with appropriate mitigation measures. Minimise uncertanties by extensive modelling of system performance with multidiscipline design software prior to manufacture. Adopt rigorous Quallity Assurance, Quality Control and acceptance criteria of equipment procurement, systems build, installation and commissioning. | 2 | 4 | 8
| 7 | Project Cost | Overrun of estimated project cost. | 3 | 4 | 12 | Develop pre CDR cost model with further work durin the CDR phase of the project to eliminate as many uncertainties as practical. Conduct cost engineering exercises during project implementation phase in conjuction with risk management to ascertain value for money solutions that meet specification. | 1 | 4 | 4
| 8 | Schedule | Overrun of estimated project timescale. | 4 | 4 | 16 | Develop a work breakdown structure and Gauntt chart schedule with resources, reviews, key milestones and critical path. Monitor and update during the project lifecycle and act when necessary to address issues to keep the project on schedule. | 1 | 4 | 4
| 9 | Key specialist staff | Availability of key specialist staff critical to delivering the project. | 4 | 5 | 20 | Identify potential single point failure risks, apply cover and succession planning where appropriate. | 2 | 5 | 10
| 10 | Safety, Health & Enviroment | SHE related issues arising during the project. | 3 | 5 | 15 | Construct facility at appropriately resourced site, enforce comprehensive SHE policy to STFC standards or better. Establish and communicate codes of practice. Procure appropriately experienced staff in Radiation Test Facility management, skills to include risk assessment, method statements, permit to work systems and RTF operational systems and methodology. | 1 | 5 | 5
| 11 | Procurement | Delays due to long lead items not ordered earlier enough. | 3 | 4 | 12 | Develop a procurement strategy for the project. Identify long lead items in the project schedule and order them with sufficent lead time as not to cause a delay. Work with and develop links to STFC procurement as a priority. | 1 | 4 | 4
| 12 | Project relevance | Requirement changes such that project performance is no longer relevant | 3 | 5 | 15 | Project involvement in wider user treatment options through expert collaboration members active in radiation biology research field | 2 | 2 | 4
| 13 | Patient input not favourable | Engagement with patient representatives produces input that is hard or impossible to reconcile with performance requirements | 2 | 5 | 10 | Early and meaningful engagement with patient representarives. Engagement with expert radiobiomedical staff with relevant experience in existing facilities and development of previous/existing facilities. | 2 | 2 | 4
| 14 | Particle source and capture | Integration of source and Lens requires compromises which impact on final performance | 3 | 5 | 15 | Early and continuing engagement with WPM teams for WP2&3 | 2 | 4 | 8
| 15 | Dose | Photo-acoustic signal cannot provide required fidelity | 2 | 5 | 10 | Use expertise in modelling of interaction to guide optimisation of detection hardware frequencies. Exploit options offered by massively parallel arrays to increase sensitivity and resolution. | 2 | 4 | 8
| 16 | Vertical beam line | Birmingham site requires compromises which reduce relevance of test | 2 | 3 | 6 | All beam performance characterisitics can be verified with existing horizontal beamline. Performance as releveant to LhARA does not depend on a working vertical beam line. | 1 | 1 | 1

## WP1-PO
Blank | Number | Name | Description | Likelihood | Impact | Score | mitigation | Mitigated Impact | Mitigated score | Comments | Significant Dates | Retirement date
| 1 | Funds | Funds awarded insufficient for full program | 5 | 4 | 20 | Prioritisation of work packages, cost/scope reduction measures within work packages | 2 | 10 | Bound to happen | Early 2022 | End project
| 2 | Staffing | Loss of critial staff effort | 3 | 3 | 9 | Dual Work Package Management team leads | 1 | 3 | Unlikely in short term, increasing risk depending on funds received | Early 2023 | End project
3

## WP6
Blank | Number | Name | Description | Likelihood | Impact | Score | Mitigation | Mitigated Likelihood | Mitigated Impact | Mitigated score | Comments | Significant Dates | Retirement date
| 1 | Fixed Field Accelerator (FFA) Performance. | FFA does not deliver parameters in performance specification. | 3 | 5 | 15 | Continue R&D on the critical item that is the FFA spiral magnet. Construct a prototype before production of 10 magnets. | 1 | 5 | 5
| 2 | Gabor lens performance | Gabor lens does not deliver parameters in performance specification. | 4 | 5 | 20 | Continue a R&D plan that involves the construction of a prototype Gabor lens and have a back up plan available that uses solenoid magnets in the place of Gabor lens. | 2 | 5 | 10
| 3 | MA Cavity construction | Insufficient availablility of Magnet Alloy (MA) Cavity suppliers. | 5 | 4 | 20 | Design and construct MA cavity in-house based on reference devices construsted by CERN, J-PARC & KURNS institutes. Component parts manufactured by industry. | 5 | 1 | 5
| 4 | Facility infrastructure | Facility infrastructure is not fit for purpose. | 4 | 4 | 16 | Include facility infrastructure design during the Conceputal Design Report (CDR) stage to provide a fit for purpose design that will inform the project cost and schedule. | 1 | 4 | 4
| 5 | Radiation protection | Radiation bulk shielding thickness, labyrinths and services penetrations are inadequate to meet specification. | 4 | 5 | 20 | Conduct radiation protection assessment during the CDR phase of the project to satisfy safety leglislation and identify construction method to inform cost and schedule. | 1 | 5 | 5