## Slide 1: Great Exhibition Road Festival of Science

## Slide 2: Initial planning [1]
Proposed time-line; for discussion:
  GERFoS: 07/08 June 2025
  February:
    Identify key elements in presentation/stand, identify leads and ask them to prepare a timeline so a schedule can be generated.
Self-imposed constraints: for discussion:
  Exhibits/stand to be ready, and set up at IC, one week before:
    30May25
  “Rehearsal session”, e.g. in Level 8 Common Room:
    04Jun25
  Actions:
    KL: find location at Imperial for test set-up of stand;
    KL: find if can set up stand, e.g., in Level 8 common room for rehearsal in afternoon of 04Jun25.

## Slide 3: Initial planning [2]
Items for stand:
  Working table next slide.
  All items considered for:
    Travelling exhibition (perhaps excluding Eve Chair and plasma demonstratory)
    Inclusion in WWW site; liaison via Pat Price, Martina Pokorna
Initial steps:
  Launch/socialise TODAY!
  Discuss present concepts, identify additional items and missing leads, by 14Feb25
  Regular planning and monitory meeting, fortnightly, 15:00, Wednesdays
    First meeting, therefore, 19Feb25.
    Report to Fortnightly
    Representation from:
      LhARA (leads of activities, local coordinator: Paul Jurj
      STFC: Clive Hill, Mitt Nathwani, …)
      CNRS, Santiago

## Slide 4: Initial topics
What | Lead | Dependencies | Notes
Virtual-reality tour of LhARA | Shields (RHUL) | CAD from C. Hill | 
Augmented-reality LhARA app | Shields (RHUL) | CAD from C. Hill | 
3D printed, assemblable model of LhARA | Shields (RHUL) | CAD from C. Hill | Coordination? Printing can be done across collaboration
Eve Chair | LEO |  | Space requirement?
Lay posters |  |  | Common template
Trifolds |  |  | Common template
Videos for stand and WWW |  |  | Common template
Confined plasma demonstrator | Bertsche (Manch) |  | Space, power
Top Trumps |  |  | 
Light-weight statistics |  |  | 
Server to share information |  |  | 
Wiki site to help organise |  |  | https://ccap.hep.ph.ic.ac.uk/trac/wiki/Research/LhARA