## Sheet1
Date: | 2024-08-04 | Issue | 1
Project | ITRF/LhARA Bridging Period | ITRF-Laser-hybrid Accelerator for Radiobiological Applications
Work package | WP2 | Source |  |  | 185 | Ave FTE cost |  |  |  | Months are measured from start of LhARA/ITRF PA1
Manager | WPMs | [8 empty] | Staff FTE by financial year; quarters are noted for calendar year
[7 empty] | 2024 |  |  |  | 2025 |  |  |  | 2026
Years | Staff | Year 1 | Year 2 | Year 3 | Total |  | Year 1 |  |  |  | Year 2 |  |  |  | Year 3
|  | 2024 | 2025 | 2026 |  |  | M19-21 | M22-24 | M25-27 | M28-30 | M31-33 | M34-36 | M37-39 | M40-42 | M43-45 | M46-48 | M49-51 | M52-54
Flag |  | Fraction | Fraction | Fraction | Fraction |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
Task | WP2 - Source
Institute | Imperial Physics
Staff | IC-Phys-Stf-1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Institute | Strathclyde Physics | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Staff | Strathclyde-Phys-Stf-2 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Staff | Strathclyde-Phys-Stf-3 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Institute | Belfast Physics | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Staff | Belfast-Phys-Stf-1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Staff | STFC-Project-Scientist | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RiskMitigationStaff | Risk mitigation effort |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
EndStaff | Staff totals | 0 | 0 |  | 0
NonStaffHd | Non staff | £k | £k
Task | Project office support
Equipment
Equipment |  |  |  |  | 0
EquipEnd | Sub-total |  |  |  | 0
RiskMitigationEquip | Cost of risk mitigation (equipment) | 0 | 0 |  | 0
TotalEquip | Eqipment total | 0 | 0 |  | 0
Consume | Consumables | 0 | 0 |  | 0
Travel | Travel |  |  |  | 0
OtherNonStaff | PPI, engagement, and outreach |  |  |  | 0
NonStaffEnd | Total non-staff costs | 0 | 0 |  | 0 | 0
Total |  |  |  | Total | 0 | 0
| Non-staff costs include VAT but not inflation. |  |  |  | 0
|  |  |  | Budget | 320
Update history
2024-07-31 | BP 1st issue C Whyte
|  | Total 2yr | 0